## Sheet1
TSBSM-76 | Develop General Security Tests | Normal | Scrapped | 10 | Unscheduled | 0
TSBSM-75 | Create/delete hubs and edit hub info | Normal | Completed | 4 | Unscheduled | 6
TSBSM-71 | Enforce upload/edit/delete permissions | Normal | Scrapped | 6 | Unscheduled | 0
TSBSM-69 | Restrict access to pages based on role/permissions | Normal | Scrapped | 6 | Unscheduled | 0
TSBSM-37 | Calendar development or third party integration | Normal | Scrapped | 8 | Unscheduled | 0
TSBSM-40 | Memories Page File Display | Normal | Scrapped | 5 | Unscheduled | 0
TSBSM-48 | Script Editor - file update with annotation | Normal | Scrapped | 8 | Unscheduled | 0
TSBSM-14 | Restructure Web App | Normal | Completed | 0 | Unscheduled | 0
Issue Id | Story | Priority | Status | Estimated Time (Hours) | Sprint Num | Actual Hours Worked
TSBSM-70 | Develop Comprehensive Account-related Unit Tests | Normal | Completed | 2 | Sprint 3 | 4
TSBSM-85 | Input sanitization: Sanitize all inputs on client and server ends to prevent NoSQL injections | Normal | Completed | 0 | Sprint 3 | 0
TSBSM-60 | Develop Front End Page for Edit Profile | Normal | Completed | 6 | Sprint 3 | 6
TSBSM-57 | Modernize the look of profile pages | Normal | Completed | 0 | Sprint 3 | 6
TSBSM-107 | Generate test database via script | Normal | Completed | 4 | Sprint 3 | 5
TSBSM-105 | sidebar display only on logged in | Normal | Completed | 6 | Sprint 3 | 5
TSBSM-78 | Admin dashboard for viewing hub info | Normal | Completed | 2 | Sprint 3 | 3
TSBSM-72 | Skeletonize and design admin/stage manager page | Normal | Completed | 4 | Sprint 3 | 4
TSBSM-62 | Add back buttons to hub subpages | Normal | Completed | 1 | Sprint 3 | 1
TSBSM-54 | Implement and Style sidebar | Normal | Completed | 0 | Sprint 3 | 8
TSBSM-55 | Encrypt MongoDB Data In Transit | Normal | Scrapped | 2 | Sprint 3 | 0
TSBSM-67 | Develop MongoDB table of preferred notification settings | Normal | Scrapped | 2 | Sprint 3 | 0
TSBSM-68 | Reroute to login page when accessing pages while not logged in | Normal | Backlog | 4 | Sprint 3 | 4
TSBSM-73 | Develop comprehensive RBAC-based Unit Tests | Normal | Scrapped | 3 | Sprint 3 | 0
TSBSM-13 | User Access Restrictions + Access Denied/Not Logged in Page | Normal | Backlog | 4 | Sprint 3 | 0
TSBSM-97 | Develop Message-related unit tests | Minor | Scrapped | 3 | Sprint 3 | 0
TSBSM-93 | Integrate Notifications for new messages | Minor | Scrapped | 3 | Sprint 3 | 0
TSBSM-83 | Develop database of message storage | Minor | Scrapped | 3 | Sprint 3 | 0
TSBSM-102 | Fix Project Website formatting | Normal | Completed | 2 | Sprint 3 | 2
TSBSM-81 | Implement Message Sending Functionality | Minor | Scrapped | 15 | Sprint 3 | 0
TSBSM-80 | Create Skeleton Message Page | Minor | Scrapped | 5 | Sprint 3 | 0
TSBSM-108 | Forgot Password Functionality | Normal | Backlog | 15 | Sprint 3 | 0
TSBSM-92 | Secure Integration: Use secure communication channels and securely store and manage API keys/secrets. Validate input and output from integrated services to prevent data breaches. | Normal | Backlog | 0 | Sprint 3 | 0
TSBSM-89 | Captcha for account/hub creation | Normal | Backlog | 0 | Sprint 3 | 0
TSBSM-87 | Authorization: Control what actions users can perform. Use access control mechanisms to enforce proper authorization, limiting access to only the necessary functionalities based on user roles. | Normal | Backlog | 0 | Sprint 3 | 0
TSBSM-86 | Secure Authentication and Authorization: To enhance security, implement multi-factor authentication (MFA) for user accounts | Normal | Backlog | 0 | Sprint 3 | 0
TSBSM-82 | Data Encryption: Implement strong encryption for sensitive data in transit to prevent unauthorized access. Utilize encryption algorithms such as AES for data protection. Look into client-side field-level encryption. | Normal | Backlog | 0 | Sprint 3 | 0
TSBSM-90 | Maximum script uploads and messages to prevent DoS | Normal | Backlog | 0 | Sprint 3 | 0
TSBSM-100 | Calendar page skeleton and design | Normal | Scrapped | 6 | Sprint 3 | 0
TSBSM-95 | Implement SMS-based notifications | Normal | Backlog | 5 | Sprint 3 | 0
TSBSM-101 | Memories page skeleton and design | Normal | Scrapped | 4 | Sprint 3 | 0
TSBSM-66 | Admin page announcement functionality | Normal | Completed | 6 | Sprint 3 | 5
TSBSM-30 | Connect Users' Updates of Own Profiles to Backend DB | Normal | Completed | 0 | Sprint 3 | 3
TSBSM-98 | Automate notifications from calendar + script updates | Normal | Scrapped | 7 | Sprint 3 | 0
TSBSM-91 | Implement email-based notifications | Normal | Completed | 5 | Sprint 3 | 0
TSBSM-79 | Host Project Online | Normal | Scrapped | 4 | Sprint 3 | 20
TSBSM-106 | Research how to make DB vendor-agnostic | Normal | Completed | 6 | Sprint 3 | 6
TSBSM-94 | Logging: Research MongoDB features for logging user changes | Normal | Completed | 0 | Sprint 3 | 0
TSBSM-65 | Admin page moderation features | Normal | Completed | 8 | Sprint 3 | 0
TSBSM-88 | Set maximum login attempts for a user | Normal | Completed | 0 | Sprint 3 | 6
TSBSM-104 | On create account page, manage errors shown to user | Normal | Completed | 2 | Sprint 3 | 7
TSBSM-99 | Add Toast Messages | Minor | Completed | 1 | Sprint 3 | 3
TSBSM-84 | Password hashing: Hash and salt passwords for secure authentication | Normal | Completed | 6 | Sprint 3 | 6
TSBSM-96 | Email validation/verification | Normal | Completed | 2 | Sprint 3 | 2
TSBSM-103 | Add functionality to create account page | Normal | Completed | 3 | Sprint 3 | 8
TSBSM-63 | File extension sanitization and maximum file size limit | Normal | Completed | 3 | Sprint 3 | 0
TSBSM-77 | Calendar event functionality | Normal | Scrapped | 6 | Sprint 3 | 0
TSBSM-74 | Calendar unit testing | Normal | Scrapped | 4 | Sprint 3 | 0
TSBSM-61 | Get rid of Google traces (CSS, attempted Google Sign-In, etc.) | Normal | Completed | 1 | Sprint 3 | 1
TSBSM-64 | Get UID from cookies to render hub info | Normal | Completed | 1 | Sprint 2, Sprint 3 | 4
TSBSM-9 | Allow Users to Create and Edit Profile and Save Changes to a New Page | Normal | Completed | 4 | Sprint 2, Sprint 3 | 6
TSBSM-23 | Integrate Professional Headshot and Resume into Profile Page | Normal | In Progress | 5 | Sprint 2, Sprint 3 | 8
TSBSM-32 | Script Editor - file upload/display | Normal | Completed | 8 | Sprint 2, Sprint 3 | 0
TSBSM-49 | Script Editor - Skeleton and page features | Normal | Completed | 3 | Sprint 2 | 3
TSBSM-58 | Develop CSS for sidebar | Normal | Completed | 1 | Sprint 2 | 0
TSBSM-59 | Develop Front End Page for Profile Display | Normal | Completed | 6 | Sprint 2 | 6
TSBSM-51 | Implement Google Sign-In for the Create Account Page | Normal | Scrapped | 40 | Sprint 2 | 0
TSBSM-22 | Implement Google Sign-In for the Login Page | Normal | Scrapped | 40 | Sprint 2 | 0
TSBSM-47 | Test Scripts for File I/O | Normal | Completed | 8 | Sprint 2 | 0
TSBSM-50 | Fix the sign-in, sign-up, and forgot password pages. | Normal | Completed | 12 | Sprint 2 | 30
TSBSM-56 | Create YouTrack for Improved Sprint Planning/Goals | Normal | Completed | 1 | Sprint 2 | 1
TSBSM-10 | Encrypt All MongoDB Data | Major | Completed | 1 | Sprint 2 | 1
TSBSM-46 | Create resources page | Normal | Completed | 4 | Sprint 2 | 0
TSBSM-45 | Create designer page | Normal | Completed | 8 | Sprint 2 | 0
TSBSM-34 | GridFS Display List of Files and Allow Users to Download | Normal | Completed | 8 | Sprint 2 | 0
TSBSM-53 | Create Test Cases for Login, Profile Tables | Normal | Completed | 1 | Sprint 2 | 1
TSBSM-26 | Convert System for Identifying Current State from Local Storage to SessionIDs | Normal | Completed | 10 | Sprint 2 | 12
TSBSM-52 | Develop Favicon for Web App | Normal | Completed | 1 | Sprint 2 | 1
TSBSM-36 | Develop Simple Helper Functions for File Uploads/Downloads | Normal | Completed | 6 | Sprint 2 | 0
TSBSM-21 | Error Handling for File Uploads | Normal | Completed | 4 | Sprint 2 | 0
TSBSM-17 | Allow Users to Create and Manage Hubs | Normal | Completed | 12 | Sprint 1, Sprint 2, Sprint 3 | 16
TSBSM-16 | Develop Fronted Container for Hubs | Normal | Completed | 0 | Sprint 1, Sprint 2 | 0
TSBSM-3 | Develop Frontend Page for Profile Creation | Normal | Completed | 5 | Sprint 1 | 5
TSBSM-6 | Set-up Node Server | Normal | Completed | 4 | Sprint 1 | 0
TSBSM-20 | Implement GridFS for MongoDB File Uploads | Normal | Completed | 8 | Sprint 1 | 0
TSBSM-12 | Set-up Google Drive Folders and Reading Files | Normal | Completed | 8 | Sprint 1 | 0
TSBSM-11 | Set-up Google Drive Uploads | Normal | Completed | 8 | Sprint 1 | 0
TSBSM-5 | Set-up React Client | Normal | Completed | 4 | Sprint 1 | 0
TSBSM-31 | Design Frontend Create Account Page | Normal | Completed | 0 | Sprint 1 | 0
TSBSM-29 | Design Frontend Forgot Password Page | Normal | Completed | 0 | Sprint 1 | 0
TSBSM-27 | Design Frontend Login Page | Normal | Completed | 0 | Sprint 1 | 0
TSBSM-8 | Develop Frontend Page for Account Creation | Normal | Completed | 0 | Sprint 1 | 0
TSBSM-7 | Integrate Create Account, Login, and Forgot Password Pages to Current React App | Normal | Completed | 0 | Sprint 1 | 0
TSBSM-4 | Design MongoDB Database to Store Profile Data | Normal | Completed | 0 | Sprint 1 | 0
TSBSM-2 | Develop MongoDB Database to Store User Credentials | Normal | Completed | 0 | Sprint 1 | 0
TSBSM-1 | Develop Frontend Page for Login | Normal | Completed | 0 | Sprint 1 | 0